7 Projects were subjected to GPT for leadership decision

PIORITIZING THE PROJECTS

| Priority | Project | Net Score | IP Score | INSIGHTS |
| --- | --- | --- | --- | --- |
| 1 | Nursery Health Demo | 8 | 1 | Easiest to execute, but low strategic impact |
| 2 | Inland Casuarina - 10% WY | 9 | 3 | Easy to implement and moderate IP value |
| 3 | Plantation Productivity Engine | 9 | 1 | Easy but limited innovation/IP |
| 4 | Subabul Improved Seed | 10 | 3 | Slightly tougher, but better impact |
| 5 | Satellite Mapping – Prakasam | 10 | 3 | Moderate complexity, innovative & useful |
| 6 | Mechanical Pulping – FDC | 11 | 5 | High IP value, but needs more resources |
| 7 | Corymbia – New Clone | 12 | 4 | Strategically strong, but resource heavy |

Updated Decision Framework

| Step | Action |
| --- | --- |
| 1 | Prioritize projects with the lowest Net Score – These are easier to implement and need fewer resources. |
| 2 | Filter based on Impact/IP – Among low-score projects, select ones with higher IP/Impact scores (Column L) for strategic advantage. |
| 3 | Select balance of short-term wins and strategic impact – Combine easy-to-implement projects with those offering long-term benefits. |
| 4 | Review high Net Score projects cautiously – Projects with high Net Score (e.g., ≥11) may need external help or phased implementation. |

Resource Optimization Strategy

| 1 | Redirect manpower and funding toward high feasibility + moderate/high impact projects (Net Score ≤10 and IP Score ≥3). |
| --- | --- |
| 2 | Reduce engagement in resource-intensive projects unless high IP/IP value is evident (e.g., Corymbia). |
| 3 | Outsource or collaborate externally for projects with high expertise or infrastructure requirements but strategic value. |

Expected Changes in Resource Allocation

| Focus Area | Allocation Change | Reason |
| --- | --- | --- |
| ✅ Top-performing low Net Score projects (e.g., Casuarina, Subabul, Satellite Mapping) | Increase or maintain resource support | These projects are feasible, impactful, and require modest effort to execute. Investing here ensures quick wins and ROI. |
| 🔍 Projects with low Net Score but low IP impact (e.g., Nursery Health Demo, Plantation Engine) | Minimal resource allocation or pilot mode | Easy to implement but limited in innovation; may be tested at small scale or combined with other initiatives. |
| 🕒 High Net Score projects (e.g., Corymbia, Mechanical Pulping) | Resources deferred, reallocated, or phased | These are resource-heavy. The head may delay them or require external funding, partnerships, or phased execution. |
| 📉 Overlapping/low-priority initiatives | Reduce or consolidate | Projects that show poor IP potential and are not core to business impact may be merged or dropped. |

Cross-Project Synergies: Combine Strengths to Maximize Impact

| Combination | Reason | Insight |
| --- | --- | --- |
| Subabul Seed + Inland Casuarina | Both aim at yield and quality improvement in tree breeding | Run parallel progeny trials with shared field teams, nutrient protocols, and coppicing observations |
| Satellite Mapping + Plantation Productivity Engine | Both deal with digital & spatial decision-making | Merge into a digital forestry intelligence platform (monitoring + recommendation engine) |
| Nursery Demo + Corymbia Clone Rooting | Nursery health tools can support clone rooting success | Use nursery health data to refine rooting protocols, improving Corymbia feasibility |

Innovation Leverage: Unlock High-IP Projects with Supporting Tools

| Enabler Project | Unlocks | Strategy |
| --- | --- | --- |
| Plantation Productivity Engine | Corymbia Clone Pulp Yield | Use early recommendations for clone-site match before large-scale rollout |
| Nursery Health Demo | Mechanical Pulping (FDC) | Optimize early-stage clonal health to improve wood uniformity for pulp specs |
| Satellite Mapping | All | Enable better site selection, growth tracking, and geo-tagged performance analysis across projects |

Portfolio Optimization: Balance Feasibility vs. Strategic Disruption

| Segment | Projects | % of Total | Risk-Reward Profile |
| --- | --- | --- | --- |
| Quick Wins (Low Score, Low IP) | Nursery Demo, Plantation Engine | 2/7 (28%) | Low risk, low reward. Use to build team morale and internal confidence |
| Scalable Impact (Medium Score, Medium IP) | Casuarina, Subabul, Satellite Mapping | 3/7 (43%) | Balanced projects – ideal for full-scale investment |
| Strategic Bets (High Score, High IP) | Corymbia, Mechanical Pulping | 2/7 (28%) | Future innovation leaders; keep R&D active but resource-aware |

Capability Development Focus

Project scores indicate that Expertise (Column H) and Scientific Infrastructure (Column I) are weaker in:

- Corymbia (score 3)

- Mechanical pulping (score 3)

Actionable Insight: Invest in capability-building (training, partnerships, lab tools) focused on tissue culture, pulping simulation, and clone rooting techniques.

Future Readiness Actions

| Insight | Action |
| --- | --- |
| Digital tools are central | Merge satellite + recommendation engines into a central digital platform (e.g. "WoodSmart AI") |
| Nursery & rooting are key to long-term IP projects | Set up a centralized rooting & nursery excellence hub to support all high-IP R&D |
| Clone-specific strategies needed | Build clone x site x product matrix to optimize matching before scale-up |

- End -