## Sheet1
KPI No | KPI Title | Key Activities / Metric | Key Highlights
KPI 1 | Progeny trial evaluation for selecting clones with >10% wood yield (WY) through genomic selection | • Selection and multiplication of top clones • MLT in 3 locations • Stability analysis across sites | • Demo planting completed at 2 locations with >90% survival • Identified promising clones M1, S1, AV55, AV56 showing ~10% higher performance than ITC1761 • Stability analysis performed across SN Padu, Alkurupadu, and Khammam
KPI 2 | Evaluation of 50 superior families from CSO to select clones with 20% WY improvement | • Seed collection and seedling selection • Establishment of progeny trials • Clonal testing across agro-climatic zones | • Multiplication completed and planting completed at Ongole • CTA trials established with 16 tree blocks and 3 replications • Families showing ~30% enhancement (GBH 32 cm, height 18 m)
KPI 3 | Evaluation of new Cj × Ce hybrid clones from 10 selected families for 20% WY improvement | • Hybridization and parental line assembly • Grafting and potted orchard development • Multi-location clonal trials | • 50 hybrid clones evaluated across 3 locations (Ongole and Anakapalli regions) • Stable high-yielding clones identified (KS4, KS9, KS2) • CE gene pool enhanced through collections from CSIRO, Cuddalore, Mandya and IFGTB
KPI 4 | Evaluation of open-pollinated putative hybrids for 20% WY improvement | • Seed collection from selected parents • Progeny evaluation and CTA establishment • Trait analysis (height, girth, bending) | • Data collection completed for progeny trials • Vigorous seedling clones selected from ITC1761 × OV15 × CH5 combinations • Evaluation based on 3-year performance underway
KPI 5 | Evaluation of Marigold and Ashwagandha intercrops in Eucalyptus plantations | • Intercropping trials at multiple locations • Growth and economic evaluation | • Marigold transplanted in 2 locations • 4 harvests completed and silaging initiated • Ashwagandha crop nearing harvest
KPI 6 | Digital Twin model for early growth prediction of Casuarina | • Integration of historical growth, weather and soil data • Development of predictive models based on accuracy more than 90%. | • Dataset created and model development completed for early wood yield prediction

## Sheet2
Milestones
| # | KPI's | Q1 | Q2 | Q3 | Q4 | Expected HIghlight
Regular KPIs | 1 | Development of next-generation Casuarina clones with ≥10% wood yield advantage over ITC1761 through GS/local selections (SSO) | * Seed collection from 50 families and raising for establishing trails (3 locations) * 3rd year Data collection (girth, height, survival %) from esisting trials (3 locations). | * Progeny trial establishment in 3 locations (Ongole, Khammam and Vizag). * Growth monitoring and data collection | * Growth analysis based on 3rd year growth data from existing trials. | Shortlist 5-10 families based on previous trials and establishment of mother bed for MLT establishment. | 3 Varieties fulfilling varietal metrices for DEMO.
| 2 | Evaluation of CSO-derived families for ≥20% WY improvement from 1761 | * Seed collection from 65 families and raising for establishing trails (3 locations) | * Multiplication for establishing trails (3 locations) | * Progeny trial establishment in 3 locations (Ongole, Khammam and Vizag). * Growth monitoring and data collection | Shortlist 5 families based on previous trials and establishment of mother bed for MLT establishment. | 5 next gen genotyes (WY 20%) fulfilling varietal metrices for MLT.
| 3 | Development of Cj × Ce hybrid clones with >20% WY and adapatibility | Assemble of CE parental gene pool and graft orchard (50) | Perform controlled crosses and hybrid seed production (30 families). | Establishment of hybrid progeny trials in 3 locations (Ongole, Khammam and Vizag). | Identify 5–8 candidate clones for business demo/MLT
| 4 | Evaluation of open-pollinated hybrids and seedling clones for >20 % WY | Complete 3rd-year evaluation ofestablished progenies trials | Select top 20 seedling clones | Establish CTA trials for selected clones (3 locations) | Growth monitoring and data collection
| 5 | Digital Twin model for early wood yield prediction in Casuarina >90% accuracy in Caruaria zones (3). | * Compile ≥120 plots data across 3 Casuarina zones * Integrate ≥5 datasets (growth, soil, weather, management, spacing) * Achieve >95% data completeness after cleaning | * Develop ≥3 ML models (RF, XGBoost, MLR) * Achieve R² ≥0.75 in initial model training * Identify Top 5 yield-influencing variables (feature importance) | * Validate model on ≥30 independent plots (3 locations) * Achieve R² ≥0.85 and RMSE ≤15% vs actual yield * Develop 1 functional dashboard (Streamlit) with ≥5 visualization modules | * Improve model accuracy to ≥90% (R² ≥0.90) * Deploy model for ≥2 pilot plantation planning decisions * Reduce prediction cycle time by ≥30% vs conventional method | Demonstrated Time / resource reduction (>30%) of Casuarina commercial release.
| 6 | BCTMP: Mill Run demonstration for Casuarina as an alternative wood | * Survey to source ≥1400 MT Casuarina wood at Ongole area with 4 year plantations | * Conduct lab BCTMP studies with different parts of tree (Bottom, middle and top) in ITC1761, CH5 and OV15 | * Conduct 1 full-scale mill trial along with Mill team and analyse the properties | * Submit business case proposal for commercial scale-up | Demonstrate ITC1761 as a viable alternative raw material with ≥90% pulp quality equivalence to FDC wood
Exploratory KPI | A | Space Breeding: Creating new variation in Casuarina seeds at stratosphere for desiarable traits of commercial intetest. | * Complete detailed project proposal (objectives, traits, partners, budget). * Identify and onboard technology partner (ISRO/private stratosphere platform/startup). * Select ≥3 Casuarina seed lots / families (≥5,000 seeds total) | * Finalize experimental protocol (altitude ≥20–30 km, exposure duration, control samples) | * Germination tests (≥500 seeds each for treated & control) | * Nursery level screening for early vigour | Establish proof-of-concept for space breeding in Casuarina, delivering ≥15% phenotypic variation